## Sheet1
PROJECT NAME: EcoFriend |  |  |  |  | Tiny Muffin Productions
WEEK OF: 23-29 Oct
TIME and WHERE: 1930 EST, Zoom
Team Member | Discussion Questions | Monday Daily Scrum | Wednesday Daily Scrum | Friday Daily Scrum
Christian Carey | What did I do since the last time we met that helped the development team meet the sprint goal? | First day of sprint | Worked on presentation script | Finalized presentation
| What will I do today to help the development team meet the sprint goal? | Work on slides for presentation | Finish script | Record presentation
| Do I see any impediment that prevents me or the development team from meeting the sprint goal? | None | Need teammates to write own intro, review assigned sections | None
Team Member |  | Monday Daily Scrum | Wednesday Daily Scrum | Friday Daily Scrum
Ed Lang | What did I do since the last time we met that helped the development team meet the sprint goal? | First day of sprint | Embedded game into own page, was pretty tricky | Researched different hosting implemenations
| What will I do today to help the development team meet the sprint goal? | Experiment with importing unity application | Looking for server/game hosting integration | Record presentation
| Do I see any impediment that prevents me or the development team from meeting the sprint goal? | None | Game currently hosted 3rd party, Firebase integration being a pain | Firebase is still a pain, seamless integration harder to achieve than anticipated
Team Member |  | Monday Daily Scrum | Wednesday Daily Scrum | Friday Daily Scrum
Kyle Lund | What did I do since the last time we met that helped the development team meet the sprint goal? | First day of sprint | Worked on presentation script | Finalized presentation
| What will I do today to help the development team meet the sprint goal? | Work on slides for presentation, Unity tutorial | Refine/scrub presentation script, prettify slides | Record presentation
| Do I see any impediment that prevents me or the development team from meeting the sprint goal? | None | Divy out speaking roles | None
Team Member |  | Monday Daily Scrum | Wednesday Daily Scrum | Friday Daily Scrum
Lily Reyes | What did I do since the last time we met that helped the development team meet the sprint goal? | First day of sprint | Player asset creation, player controller script | Team logo design
| What will I do today to help the development team meet the sprint goal? | Player asset creation, player controller script | Logo design | Record presentation, debug jittering in-object collision
| Do I see any impediment that prevents me or the development team from meeting the sprint goal? | None | Point lighting not working as intended | Quality vs time tradeoff for asset development