## Sheet1
PROJECT NAME: EcoFriend |  |  |  |  | Tiny Muffin Productions
WEEK OF: 6 Nov - 12 Nov
TIME and WHERE: 1930 EST, Zoom
Team Member | Discussion Questions | Monday Daily Scrum | Wednesday Daily Scrum | Friday Daily Scrum
Christian Carey | What did I do since the last time we met that helped the development team meet the sprint goal? | Cleaned up and submitted test case doc. Looked into upcoming sprint presentation assignment | Created outline for sprint 1 presentation, divied up slides, added images | Wrote presentation script, finalized presentation slides, worked on test cases
| What will I do today to help the development team meet the sprint goal? | Set up our kanban board, populate it with tasks, begin working on outline of sprint 1 presentation | Write presentation scripts, add more images | More test cases
| Do I see any impediment that prevents me or the development team from meeting the sprint goal? | None | Awaiting guidelines for presentation | Getting jest working
Team Member |  | Monday Daily Scrum | Wednesday Daily Scrum | Friday Daily Scrum
Ed Lang | What did I do since the last time we met that helped the development team meet the sprint goal? | Implemented NextAuth, created sign in component | Implemented various templates for website | Explored database options
| What will I do today to help the development team meet the sprint goal? | thinking about backend database and tying it into website, UI design | Database implementation for teams and blog functionality | Create learn and about pages, explore Prisma integration
| Do I see any impediment that prevents me or the development team from meeting the sprint goal? | None | None | None
Team Member |  | Monday Daily Scrum | Wednesday Daily Scrum | Friday Daily Scrum
Kyle Lund | What did I do since the last time we met that helped the development team meet the sprint goal? | Implemented sign up and login with an email/password | Implemented login/sign up with google/github | Implemented password and username changing
| What will I do today to help the development team meet the sprint goal? | Implement sign on/login with google/github | Implement account maintenance functions | Implement account creation
| Do I see any impediment that prevents me or the development team from meeting the sprint goal? | Need team input on database schema | Standard learning curve | JS sucks!
Team Member |  | Monday Daily Scrum | Wednesday Daily Scrum | Friday Daily Scrum
Lily Reyes | What did I do since the last time we met that helped the development team meet the sprint goal? | Researched best method of version control for the game - Github vs. Plastic. Worked on components for enemy NPCs and damage. | Enemy damage function, completed NPC's, modified PlayerController script to add invincibility for a set time to player | 2 Scripts, (enemyController, damageZone), axe man assets
| What will I do today to help the development team meet the sprint goal? | Need to continue working on enemy NPCs. Get started on designing the environment for the level. | Projectile implementation, start working on full build for functionality demo | Ax man animation, player animation
| Do I see any impediment that prevents me or the development team from meeting the sprint goal? | Difficult deciding on the version control due to limitations of number of users, etc. | None | Time