## Sheet1
PROJECT NAME: EcoFriend |  |  |  |  | Tiny Muffin Productions
WEEK OF: 30 Oct - 4 Nov
TIME and WHERE: 1930 EST, Zoom
Team Member | Discussion Questions | Monday Daily Scrum | Wednesday Daily Scrum | Friday Daily Scrum
Christian Carey | What did I do since the last time we met that helped the development team meet the sprint goal? | Starting testing assignment | Worked on test cases | Finished test cases
| What will I do today to help the development team meet the sprint goal? | Write more test cases | Continue working on test cases | Review test cases and prettify for submission
| Do I see any impediment that prevents me or the development team from meeting the sprint goal? | Lack of clarity in testing assignment (it don't make no sense!) | So many user stories to test! | None
Team Member |  | Monday Daily Scrum | Wednesday Daily Scrum | Friday Daily Scrum
Ed Lang | What did I do since the last time we met that helped the development team meet the sprint goal? | Nothing | Implemented firebase integration | Researched authentication systems
| What will I do today to help the development team meet the sprint goal? | Get website running on server, work on website test cases | Build blog pages | Implement swap to next auth
| Do I see any impediment that prevents me or the development team from meeting the sprint goal? | None | No | None
Team Member |  | Monday Daily Scrum | Wednesday Daily Scrum | Friday Daily Scrum
Kyle Lund | What did I do since the last time we met that helped the development team meet the sprint goal? | Nothing | Edited login, created the sign up page | Discovered a dozen ways not to implement login/sign up functions. Activated authentication functions in firebase
| What will I do today to help the development team meet the sprint goal? | Build login page | Tying firebase integration from Ed into an actual login/sign up function | Continue tying to integrate firebase into an actual login/sign up function
| Do I see any impediment that prevents me or the development team from meeting the sprint goal? | Not knowing how to build a login page | Not knowing how to do that | Lack of time to go through tutorials
Team Member |  | Monday Daily Scrum | Wednesday Daily Scrum | Friday Daily Scrum
Lily Reyes | What did I do since the last time we met that helped the development team meet the sprint goal? | Enemy script and art | Enemy asset creation, researching file sharing for unity | Progress on URP, additional enemy asset creation
| What will I do today to help the development team meet the sprint goal? | Enemy asset creation, researching file sharing for unity | Install universal render pipeline (lighting) into project | Port unity assets to github, implement test cases for game
| Do I see any impediment that prevents me or the development team from meeting the sprint goal? | Time | Experience in URP/lighting | Nope