## Sheet1
PROJECT NAME: EcoFriend |  |  |  |  | Tiny Muffin Productions
WEEK OF: 13 - 19 Nov
TIME and WHERE: 1930 EST, Zoom
Team Member | Discussion Questions | Monday Daily Scrum | Wednesday Daily Scrum | Friday Daily Scrum
Christian Carey | What did I do since the last time we met that helped the development team meet the sprint goal? | New Sprint | Researched sonar cloud/static code analysis, created boss level environment | Ran static code analysis
| What will I do today to help the development team meet the sprint goal? | Research sonar cloud/static code analysis | Run static code analysis | Bug squashing! And also code smells
| Do I see any impediment that prevents me or the development team from meeting the sprint goal? | None | None | None
Team Member |  | Monday Daily Scrum | Wednesday Daily Scrum | Friday Daily Scrum
Ed Lang | What did I do since the last time we met that helped the development team meet the sprint goal? | New Sprint | Built team page plus 3xcomponents | Integrate Teams page with API
| What will I do today to help the development team meet the sprint goal? | Build team page | Integrate teams page w/ API's | Assist with website bug squashing, work compile errors to deploy
| Do I see any impediment that prevents me or the development team from meeting the sprint goal? | None | None | None
Team Member |  | Monday Daily Scrum | Wednesday Daily Scrum | Friday Daily Scrum
Kyle Lund | What did I do since the last time we met that helped the development team meet the sprint goal? | New Sprint | Built team schema, built first draft of various teams API's, hunted for assets | Experimented with first website deployment, began creating title scene for game
| What will I do today to help the development team meet the sprint goal? | Tile asset search, assist on team page backend | Standby for teams API issues, familiarize self with game | Finish title scene, assist on other game things
| Do I see any impediment that prevents me or the development team from meeting the sprint goal? | None | None | None
Team Member |  | Monday Daily Scrum | Wednesday Daily Scrum | Friday Daily Scrum
Lily Reyes | What did I do since the last time we met that helped the development team meet the sprint goal? | Fixed bug on enemy animation script | Implemented game version control | Squirrel animation, squirrel attack behavior script, created projectile assets/script
| What will I do today to help the development team meet the sprint goal? | Game version control, complete player animation scripts | Review assets, program camera, implement player projectile functions | Fit pieces together, camera behavior, complete game world
| Do I see any impediment that prevents me or the development team from meeting the sprint goal? | None | None | None