## Sheet1
PROJECT NAME: EcoFriend |  |  |  |  | Tiny Muffin Productions
WEEK OF: 27 Nov - 3 Dec
TIME and WHERE: 1930 EST, Zoom
Team Member | Discussion Questions | Monday Daily Scrum | Wednesday Daily Scrum | Friday Daily Scrum
Christian Carey | What did I do since the last time we met that helped the development team meet the sprint goal? | Sent recipe for tatertot casserole, bug squashing | Fixed some code smells, worked on presentation | Finished presentation, squashed some code smells, continued work on documentation
| What will I do today to help the development team meet the sprint goal? | Work through code smells, continue work on presentation and final report | Continue slides and scripts, more code smells | We Done!
| Do I see any impediment that prevents me or the development team from meeting the sprint goal? | Not enough tatertot casserole | None | None
Team Member |  | Monday Daily Scrum | Wednesday Daily Scrum | Friday Daily Scrum
Ed Lang | What did I do since the last time we met that helped the development team meet the sprint goal? | Finished teams GET/POST API | Attempts to rebase branch | Implemented create and join teams, squashed code smells
| What will I do today to help the development team meet the sprint goal? | Integrate team creation page into website | Code smells, props read-only error, recreate branch with team functionality | We Done!
| Do I see any impediment that prevents me or the development team from meeting the sprint goal? | None | More git issues | None
Team Member |  | Monday Daily Scrum | Wednesday Daily Scrum | Friday Daily Scrum
Kyle Lund | What did I do since the last time we met that helped the development team meet the sprint goal? | Squashed bugs, got website to deploy, created title/splash/credits scene | Added comments to code and worked on fixing code smells | Worked on documentation
| What will I do today to help the development team meet the sprint goal? | Work on presentation/final report | Work on presentation/final report | We Done!
| Do I see any impediment that prevents me or the development team from meeting the sprint goal? | None | None, git is a pain | None
Team Member |  | Monday Daily Scrum | Wednesday Daily Scrum | Friday Daily Scrum
Lily Reyes | What did I do since the last time we met that helped the development team meet the sprint goal? | Level 1 complete | Progress on squirrel behavior, end-level script | Completed tutorial screen, cleaned up level 1, completed level 2, added audio effects
| What will I do today to help the development team meet the sprint goal? | Additional levels | Fight git issues, more squirrel behavior, bug checking on end-level script | We Done!
| Do I see any impediment that prevents me or the development team from meeting the sprint goal? | None | LFS on git is pain | None